## Slide 1: ManageEngine Technical Delivery Roadmap
Oct 2026 – Jun 2027
Phases
Releases
Phase 1 Oct 2026 – Dec 2026 · Release 1
Phase 2 Jan 2027 – Jun 2027 · Releases 2 & 3
Release 1 Oct 2026 – Dec 2026
Release 2 Jan 2027 – Mar 2027
Release 3 Apr 2027 – Jun 2027
Interface Category
Oct-26
Nov-26
Dec-26
Jan-27
Feb-27
Mar-27
Apr-27
May-27
Jun-27
Future / TBD
Identity &
User Management
Entra ID
Active Directory
Workday
UKG
Okta
Communications &
Service Channels
Teams
Sinch SMS
Genesys
Asset & Configuration
Management
Intune
SCCM
Lansweeper
VMware vSphere
Azure Resource Graph
NetBox
Monitoring, Security &
Operations
Azure Monitoring
PRTG
CrowdStrike
LogRhythm
Seamless SOC
Medigate
Tenable
Cloud, Integration &
Automation
Azure API Management
Azure DevOps
Copilot
Azure OpenAI
Vendor & External
Services
NTT CMDB
HP
NTT
Optus
Cognizant
Accenture
Ready Contracts
Rhapsody
Data Migration
Cortex Archive
Cherwell
ME Asset Discovery
Agent & Agentless Pilot
Agent & Agentless Rollout
Milestone Timeline
Oct-26
Nov-26
ME SDP Release 1 Go Live
Agent & Agentless Pilot
Dec-26
Agent & Agentless Rollout (may slip to Jan)
Cherwell Shutdown
Jan-27
Golden Asset Record configured (may slip to Feb)
Feb-27
ME SDP Release 2 Go Live
LivePro Shutdown
Mar-27
Apr-27
May-27
ME SDP Release 3 Go Live
Jun-27
Note: Items are shown in the month of their planned end date (as per “End” column).
Release 1
Release 2
Release 3
TBD
Notes: Source: ManageEngine_Interface_Tracker_v4.xlsx. Each interface is placed in the month of its planned End date and coloured by its Release column. Phase 1 = Release 1 (Oct–Dec-26); Phase 2 = Releases 2 and 3 (Jan–Jun-27). Milestone markers sit at their date within the month. Roadmap v2 edits: Intune, SCCM, Lansweeper, NTT CMDB and HP (now under Vendor & External Services) finish Dec-26 as Release 1 items; VMware vSphere, Azure Resource Graph and Azure API Management finish Jan-27; milestones at month end. Phase = TBD items sit in the Future / TBD column. Updated per 28-Oct-2026 call with Jacinta Undy: release windows realigned; agent/agentless pilot (Nov) and rollout (Dec, contingency Jan) clubbed; Tenable and NetBox moved to TBD; CMDB/asset-list feeds (Intune, SCCM, Lansweeper, NTT CMDB) moved to start of Release 2 (Jan-27); Golden Asset Record milestone added for end of Jan-27 (contingency Feb). The Golden Asset Record depends on the asset integrations, which depend on the full agent/agentless rollout.