## Slide 1: ManageEngine Technical Delivery Roadmap
Oct 2026 – Jun 2027
Releases
Release 1 Oct 2026 – Dec 2026
Release 2 Nov 2026 – Feb 2027
Release 3 Jan 2027 – May 2027
Interface Category
Oct-26
Nov-26
Dec-26
Jan-27
Feb-27
Mar-27
Apr-27
May-27
Jun-27
Future / TBD
Identity &
User Management
Entra ID
Active Directory
Workday
UKG
Okta
Communications &
Service Channels
Teams
Sinch SMS
Genesys
Asset & Configuration
Management
Intune
SCCM
Lansweeper
NetBox
VMware vSphere
Azure Resource Graph
HP
Monitoring, Security &
Operations
Azure Monitoring
PRTG
CrowdStrike
Tenable
LogRhythm
Seamless SOC
Medigate
Cloud, Integration &
Automation
Azure DevOps
Azure API Management
Copilot
Azure OpenAI
Vendor & External
Services
NTT CMDB
NTT
Optus
Cognizant
Accenture
Ready Contracts
Rhapsody
Data Migration
Cortex Archive
Cherwell
ME Asset Discovery
Agent based Pilot
Agentless Pilot
Agent based Rollout
Agentless rollout
Milestone Timeline
Oct-26
Nov-26
ME SDP Release 1 Go Live
Dec-26
Agent based Pilot
Agentless Pilot
Cherwell Shutdown
Jan-27
Feb-27
Agent based Rollout
Agentless Rollout
LivePro Shutdown
ME SDP Release 2 Go Live
Mar-27
Apr-27
May-27
ME SDP Release 3 Go Live
Jun-27
Note: Items are shown in the month of their planned end date (as per “End” column).
Release 1
Release 2
Release 3
TBD
Notes: Source: ManageEngine_Interface_Tracker_v2.xlsx. Each interface is placed in the month of its planned End date and coloured by the release window that month falls in (≤Dec-26 Release 1, Jan–Feb-27 Release 2, Mar–May-27 Release 3). Phase = TBD items sit in the Future / TBD column.